## Instructions
RISK MANAGEMENT PROCESS OVERVIEW
RISK MANAGEMENT CONCEPTS
| RISK IDENTIFICATION | What might go wrong?
Background information (e.g. lessons learned, audit information if available)
Consider team´s experience
| RISK ANALYSIS | what is the problem and what is causing it
| RISK EVALUATION | Use the risk matrix to evaluate the risk
First identify probability of issue occuring
Then assess the impact should it occur
Obtain score in grid and adjust based on likelihood of detection - i.e. easy to detect, risk is lower and overall risk may be reduced
| RISK CONTROL | Accept: Acknowledge and accept the existence of a particular risk or residual risk. There are risks where we can do nothing or all has been done and there is residual risk which needs to be accepted. If the risk is small and does not have a significant impact we can accept the risk
Avoid: Avoid the risk. Risk avoidance refers to prevention of risks from happening. For example, not flying to avoid the plane being hijacked
Reduce: Implement actions to minimize the impact or likelihood of the risk. For example contingency plan of having sites ready to start.
Transfer: transfer risk or paying someone else to accept the risk. For example insurance.
| COMMUNICATE RISK | Prioritise risks and assign mitigation owner and deadline
Minute risk assessment and distribute
Ensure relevant risks are considered in vendor oversight plan to ensure focus by vendor and oversight
Ensure relevant risks are considered in monitoring plan to ensure focus by monitor
Escalate issues as per below and when high risk action plan needs to be prepared
Individual risks
|  | low | manage within team
|  | medium | Escalate to functional / line manager
|  | high | Escalate Manager +1
| REASSESS RISK | Re-assess risks on a very regular basis to ensure risks are managed on an ongoing basis. As a minimum this should happen at the following times
At draft protocol stage
After SIV
During recruitment
At DB lock
Check if issues raised warrant an update to other documents, e.g. Monitoring Plan, Vendor Oversight Plan
Note on K30: Description should be objective and clear X "IMP transportation issues" OK "Temperature excusion during transportation leading to IMP unsuitable for use" X "Database access issues" OK "Major (extended period/recurring) database access issues leading to delays in data entry" X "Staff turnover issues" OK "There is turnover of key staff as defined in the contract in the setup phase of the study, leading to loss of knowledge and potential delays early in the study"

## Risk Assessment
RISK MANAGEMENT PLAN
Study Code |  |  |  | OVERALL STUDY RISK SCORE AFTER MITIGATION (please mark one option below with an "X") |  |  |  | Assessment team (name, role, function)
Assessment date and version |  |  |  | X | Low - No High scores and less than 50% Medium (LM/HM) scores
Medium - maximum one High score and/or more than 50% Medium (LM/HM) scores
High - more than one High score
No. | Department/ Function | DESCRIPTION OF RISK | PRE MITIGATION ASSESSMENT | [6 empty] | MITIGATION | POST MITIGATION ASSESSMENT | [6 empty] | Owner | Action date | Action | Status
|  |  | Probability |  | Impact |  | Detectability |  | Risk Score |  | Probability |  | Impact |  | Detectability |  | Risk Score
|  |  | Score | Brief rationale for selected score | Score | Brief rationale for selected score | Score | Brief rationale for selected score |  |  | Score | Brief rationale for selected score | Score | Brief rationale for selected score | Score | Brief rationale for selected score
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
RMP VERSION CONTROL HISTORY
Version number |  | Date
1
2
3
4
5
6
DO NOT DELETE ROWS FROM THIS POINT ON
Low
Medium
High
0
2
4
Almost Certain
Likely
Possible
Unlikely
Rare
Insignificant
Minor
Moderate
Major
Severe
L
LM
HM
H
Note on E2: Definitions for guidance only tick one opion and escalate as per instructions
Note on J8: see risk matrix next sheet
Note on D9: Almost certain - Will undoubtedly happen, possibly frequently Likely - Will probably happen, but it is not a persisting issue/circumstances Possible - Might happen occasionally Unlikely - Do not expect it to happen but it is possible it may do so Rare - This will probably never happen
Note on F9: Insignificant - no or negligible impact on key aspects* of the study Minor - could impact non key aspects* of the study Moderate - could impact some non key and some key aspects* of the study, or it could impact certain non key aspects that are/may be linked to key aspects (domino effect) Major - could impact key aspects* of the project Severe - could directly lead to unsuccessful project *Examples of key aspects – timelines, subject safety, IMP efficacy, study objective/endpoints, data integrity, overall quality, etc
Note on H9: Low (Risk increases) Moderate (No change to risk) High (Risk decreases)

## Risk Matrix
Risk Matrix
|  | L | =Low | LM | =Low Medium | HM | =High Medium | H | =High
Probability x Impact |  | IMPACT
|  | Insignificant |  | Minor |  | Moderate |  | Major |  | Severe
PROBABILITY | Almost certain | LM |  | HM |  | H |  | H |  | H
| Likely | LM |  | LM |  | HM |  | H |  | H
| Possible | L |  | LM |  | LM |  | HM |  | H
| Unlikely | L |  | LM |  | LM |  | LM |  | HM
| Rare | L |  | L |  | L |  | LM |  | LM
When detectability is high, risk reduces / When detectability is low, risk increases

## Sheet1 (hidden)
low | rare | insignificant | Blinding
medium | unlikely | minor | Data Management
high | possible | moderate | Ethics submissions / Approvals
| likely | major | Investigational product
| almost certain | severe | Medical Writing
Monitoring
Other
Recruitment / Retention
Regulatory
Statistcs
Study Outcome
Subject safety
Technology
TMF and Archiving
Training
Translations
Vendor
Vigilance